## Sheet1
Feedback No | User | Comment | Possible to change Y/N | Students response | Change made date | Complete | Further Question
1 | JMcB - Iphone via Expo project | User instructions pop up - i.e how to add food to plate i.e double click so it turns yellow (or mention in help section), then click on plate to add % | N | Best solution is to use the help screen provided in the navbar, but we will revamp this to contain more pertinent information | 2019-08-03
2 | JMcB - Iphone via Expo project | Using on Iphone - it kept buffering every 5 min - see screen shot - it takes you out of plate page and displays this - fustrating - why is this? | Y | This is a quirk in Expo's design, but should not persist. | 2019-08-03 | Y | 17:43 13/03 buffered 5 times in a row - is that because you are updating while I am playing? should I stop till you are finished?
3 | JMcB - Iphone via Expo project | Foods - most frequently used list appear at the top? Save keep searching through irrelevant foods or add to favourites button | Y | Implemented a "recently added" foods section when no search is being performed. | 2019-08-03 | Y | Fantastic thanks
4 | JMcB - Iphone via Expo project | love the link to choose my plate.gov. - well done | Y | Thank you :) | 2019-08-03 |  | sorry - just realised this is an american link - is there a UK equivalent? I presume we dont need permission to link to websites? I'll check with Mike - www.nhs.uk/live-well/eat-well
5 | JMcB - Iphone via Expo project | wee glitch when I added, bread, butter and eggs to fill the plate to 100% I then tried to add in coconut oil - the I tried to reduce the eggs to 95% and add the coconut oil but all the % changed at the same time i..e I moved coconut up/down the others all moved up/dowm then I got an syntex error and the app stopped working I had to switch off and log in again, after logging in again it buffered x 2 in 3 min see screen shot | Y | This is not a glitch: when changing the percentage of foods the other sliders must also increase/decrease as the maximum allowance is also changing. Syntax error shown on the screenshot has also been fixed. | 2019-08-03 | Y
6 | JMcB - Iphone via Expo project | On submission of plate the list comes up of nutrients etc which is great - but makes no sense. Can this also be displayed of % of daily dosage or what 1/3 of % of daily dosage should be? i.e. = % of your daily dosage or daily dosage should be etc - because to be honest I dont think I would know or what I need to improve upon otherwise? | Y | Percentages added based on how much of the daily recommended amount a player has on their plate (can be more than 100%) | 2019-08-03 |  | is this 100 % daily recomended allowace/intake or a 1/3 of the daily amount - just to clarify - might need to make that clear on the screen - can you put a message above saying 1/3 or 100% of allowance- it is is a 100% of daily intake can you put a header above the Your Plate Nutrients to say this meal = 1/3
7 | JMcB - Iphone via Expo project | Score page - a description of how points are calculated / awarded? Is a high score good? I don’t understand what the aim / target is. Should we have something here also saying or hinting how to improve? | Y | Maximum score added so as to suggest to the player how far away from a perfect score they are. This alongside with the percentages added above and warning messages on the score screen (shown right) should give ample information for a player to improve, however I will try to think of further improvements | 2019-08-03 |  | Still not to sure on this, initially a low score is bad and a high score v good? a wee statement like this would be good if that is the case.
8 | JMcB - Iphone via Expo project | Buffering again and again - too many and fustrating then got this message and I cannot get back into the app - no matter how many times I log in and out/ refresh just keep seeing a screen like this. So I have submitted a plate but not been able to change it or save it or test it further | Y | Similar to issue #2, should hopefully no longer occur | 2019-08-03 | y
9 | JMcB - via Android | cannot add food via the icons round the side i.e. Apple bread drink can | Y | Currently being implemented
10 | JMcB - Iphone via Expo project | so I have 29% eggs and 71% boiled Brocoli I get a message saying my Vt B1 levels are too low, no message saying anything else is within range or good? I don’t feel I am learning anything. Can what is good be added in. | Y | Will add messages for nutrients that are especially good, current assumption is if there is no warning message then you are somewhat close to the range expected |  |  | great thanks the colour coding is great and very useful as is the well done message. not too sure about the word dangerously though - its a bit severe. is it easy to replace with "too low" or just "low" if just under?
11 | JMcB - Iphone via Expo project | Saved plates not displaying | Y | Currently being implemented |  |  | Excellent - possible for future development but can I delete only selected plates not them all?
12 | JMcB - Iphone via Expo project | be to call the saved plates a name i.e chicken n mash or eggs n chips | Y | Player's can name their plates now
13 | JMcB - Iphone via Expo project | Is it possible to have a clear your plate button - quite cumbersom after several goes and not imrpoving scores so rather start again | Y | This is already implemented but had a slight bug, fixed now (button is at the bottom of the food editting view. |  | Y
14 | JMcB - Iphone via Expo project | 21 % potatoes mashed, with butter, 61% peas in unsalted water, 18% chicken breast/steak coated/baked = 558.7 calories etc. Submitted: score 7850 after 4 adjustments - score Is coming down - but what is target, carbs are too high - but how much over am I? a pop up tip or bar chart or % | Y | Can add a % of how much over/under a player is |  |  | Great but will need to know if it is over or under.
15 | JMcB - Iphone via Expo project | in relation to point 13, I tweaked the plate got score down to 7143, making 6 adjustments, 15% potatoes, 10% chicken, 75% peas calcium score is too low - pop up tip for suggested foods with whatever is lacking? I then added a glass of milk reducing peas to 51% but how much milk am I drinking - would it be possible to display gramms next to the % so you get a rough idea of what is being consumed. (on the food list /back to plate bit) | N | Suggested foods would be a cumbersome task that wouldn't fit the short time we have remaining. |  |  | is it possible to build in a pop up that just lists foods that cotain XX I just googled vitamin B1 and got a list of foods - if this is technically to difficult then fine or include a link - see links in row 44?
16 | JMcB - Iphone via Expo project | So from this I get that you hardly eat any protien/carbs and just about have a full plate of veg. Unless there is tips guidance on substitutions after maybe many attempts how to people increase and know about foods that fill them up for longer. Was GI index impossible to do or only impossible due to time constraints? | N | Due to how different two databases of data would be, we would have to manually compute GI for each food - definitely impossible due to time constraints |  | FD | ok but possible for future development good to know. Thanks
17 | JMcB - Iphone via Expo project | 13% sunflower seeds, 16% pumpkin seeds, 27% cherries, 44% greek youghurt = 1183.8 calories score of 963 point? How is this low? Calories, too high, fats too high, protien too high, sugar too high, satfat too high; b1 too low, b9 too low - after tweaking 10% sun flower, 9% pumpkin, 46% cherries, 35% youghurt - 885.5 calories and 3693 points? why now only sugars high, sat fat, high, b1, low, b9 low but not telling me what is good
18 | JMcB - Iphone via Expo project | even try compare one food. i.e 100% greek style yoghurt. How much is that - I am getting 665 kals but how many grms? And score 3420 points: Now I add cherries 50% = 452.5 kcal and I score 6084 points but this is a bit better nutients wise - in terms of calories but other are still to high - but i dont know if they have went up or been reduced by any so dont know if I add more cherries that will reduce the fat - (which I know it will) but useing this as a simple example. how to folk know what item changes things apart from their scores. don’t suppose there is a way of comparing your tweaks in a visual way i.e. a chart or something, difficult to remember these numbers and text from ageneral user point of view and seems too complicated. the concept is great and I can see it working - just need to make it a bit more user friendly visually so they can learn from it. | N | A good idea - would like to implement a chart that shows how your tweaked plate is different from your original plate, but would be too much work to implement in a week |  | FD | Ok something to think for futher development then as I think really important for learning.
19 |  | pick a food you eat and see if you can learn anything from it being 100%. Then add something else in - see what you learn and why / how you learned.
20 | JMcB - Iphone via Expo Project | Ok question, if I have a full plate of eggs, or a full plate of youghurt for example, how much is that? is it 2 eggs or 7 eggs - I am not sure how we display this, i.e. say I have a fried egg sandwich. is that 50% egg and 50% bread - then how many slices of bread and how many eggs. | N | Mike's specification requests we display information based on how it looks on a plate (i.e. percentages) not based on the number of items |  | FD | Understand but still not clear to me and therefore I presume others. Need to think about this for further development
21 | JMcB - Iphone via Expo Project | On submission of plate - too high or too low no indication of how far out - dont suppose you could add in a red/amber/green square/colour to give a hint on what is too far out to show if you are improving or not
22 | JMcB - Iphone via Expo Project | Is it possible to add sounds? i.e. when successfully added something to the plate | N | Time Constraints |  | FD | Ok future development
23 | JMcB - Iphone via Expo Project | Is it possible to add sounds? i.e. when increasing/decreasing the amount like a wee beep per % | N | Time Constraints |  | FD | OK future development
24 | JMcB - Iphone via Expo Project | Under saved plates the option dark background appears | Y | Saved plates screen now added | 2019-12-03 | y | Excellent.
25 | JMcB - Iphone via Expo Project | Need more detailed info on the help page, I will discuss intro and explaination with Mike / Laura. can you create a rules page in addition | Y | Help screen is now more detailed | 2019-12-03 |  | see row 39 - dont worry if you are out of time now
26 | JMcB - Iphone via Expo Project | Help page ...The plus button allows you to look for foods - there is no plus button - its a search? then the plus minus button appear on the slider | Y | Help screen is now more detailed/has been fixed for the new updates we've made | 2019-12-03 |  | ok thanks
27 | JMcB - Iphone via Expo Project | can you create a rules page in addition to the help page - I think more explanation around points/tweaking and 1/3 of a meal etc s required | Y | We can integrate this onto the help screen | 2019-12-03
28 | JMcB - Iphone via Expo Project | As the recently selected list grows - is it too difficult to display them in alphabetical order? - easier for scrolling through | Y | The most recently searched item always shows up at the top of the list until you restart the app, then it lists it alphabetically | 2019-12-03 | Y | ok fab
29 | JMcB - Iphone via Expo Project | it is possible to delete something from the recently selected list? | Y | Added a button in settings to clear all foods in the recently searched list | 2019-12-03 |  | Dont want to clear all, just the random stuff that I added in to try make a balanced plate - the frequently used list is brill and it would be cumbersome if all previously searched items were deleted. I undertand if it is techincally to complex to do individual items but something to bear for tweaking after project
30 | JMcB - Iphone via Expo Project | Is it possible to search recently selected list and/or main list - as your list of favoruites grow this would be a nice function | N | Time Constraints - Would need an entirely new search function |  | FD | OK
31 | JMcB - Iphone via Expo Project | I think this is linked to something above that you said couldnt be done in time frame?? but would be useful. to be able to compare 100% cheese with 100% mozarella - I think this will help people see how to improve on one food item. i.e. compare 100% full fat milk with 100% skimmed milk; or 100% boiled potatoes with 100% sweet potatoes; 100% white rice with 100% brown rice - etc do you understand where I am coming from? Just checking its not something else easily implemented. | N | Time Constraints - Very possible and a good feature idea, but would need either a completely new screen to be added or the score screen to be heavily changed. |  | FD | OK
32 | JMcB - Iphone via Expo Project | Can you add iron into the nutrients? | N | Time Constraints - would require new code to parse the mccance database |  | FD | ok - future development
33 | JMcB - Android phone & Iphone | colour grey of "help" "saved plates" and "login" at bottom of screen make it look like these options are not available. | N | Standard phone convention: they highlight blue when selected, this way they stand out and the user knows which tab they're on |  | y | ok
34 | JMcB - Android phone | The apple, bread, youghurt, drink icons have a plus sign but not working at present i.e. cannot add | Y | Side items now implemented | 2019-12-03 |  | Doesnt seem like these affect the calories or nutrients or scores?
35 | JMcB - Iphone via Expo Project | The apple, bread, youghurt, drink icons dont have a plus sign | Y | Removed plus icon as they seemed unnecessary and the greyed out foods are intuitive enough | 2019-12-03 |  | OK but see row 34
36 | JMcB - Android phone | Unable to clear plate although it does reduce all items to 0% but all foods are still listed below. On Iphone it clears the list and lets you start anew. |  |  |  |  | This seems to have been resolved after re-fresh.
37 | JMcB - Iphone and Android | While searching e.g "low GI Bread" the return = no foods found. - pop up to tell user just to type in bread - and not to be too specific if no foods found message appears? | Y | Added more informative error message | 13/03/2019 | FD | ok
38 | JMcB - Iphone and Android | Possibility of an icon next to the score to indicate good bad or mediocre i.e wooden spoon for rubbish, a rosette red/yellow/green or champion cup - to indicate how good/bad the score is - might help reduce the confusion over the score. | Y | Added traffic light colours to score | 13/03/2019 | Y | Fantastic - this makes a huge difference
39 | JMcB - Iphone and Android | Intro? The aim of this game is to see how good you are at preparing a healthy balanced meal. The optimal score is 13,000 points – if you achieve this score you have successfully created the optimum requirement of calories and nutrients, on your first attempt. (MAX is this correct?) Each plate you create equates to 6-800 calories 1/3 of your daily recommended intake. This is based on the assumption you eat 3 x meals a day comprising of a total of 1800- 2400 calories. (MAX - I’m unsure of this = confusing – recommended amounts for women are 1800 and men are 2500, how do we know what the app is working out? can you clarify or do I need to speak to Mike to clear up?) Add your ingredients to the plate to see if it is balanced, if not make tweaks, and try improve upon the proportions/calories and nutrients. |  | 13000 points is the maximum possible, that means you're getting the perfect amount of every nutrient. For calories and several other nutrients, there is a range that defines what your nutrient intake for that meal should be. For example, anywhere between 16-25g of fat on your plate is considered a "perfect" score. This then allows people of all sorts to aim for the same goals.
40 | JMcB - Android | The clear plate bar is too large in comparrison to the last +- increase food button and every time - I try to increase/decrease the last item I keep getting clear plate message - can the clear plate be made into a button rather than if you touch anywhere the clear screen being activated? | Y | Clear button lowered and touch radius decreased - should be harder to accidentally press now
41 | JMcB - Iphone and Android | I am finding it very difficult to get a balanced plate and until there is some guidance or green/red coding or advice etc showing you where you are doing well and where not - I cant see how to improve/ make it slightly easier as if its too difficult people will give up. need to strike a happy medium. if none of the suggestions can be implemented to help the user can there be an example page of a balanced plate showing optimum score, not sure if this is easy to implement or not. | Y | Colour coding added to score, with quick testing it is not too difficult to get a "green" score with a few tweaks. |  | y | This is great, makes a huge difference
42 | JMcB Iphone and Android | Link to Vitamin and Mineral - show foods that contain X, Y Z: https://www.nhs.uk/conditions/vitamins-and-minerals/ Link to Sugars - https://www.nhs.uk/live-well/eat-well/how-does-sugar-in-our-diet-affect-our-health/ Link to Calories- https://www.nhs.uk/common-health-questions/food-and-diet/what-should-my-daily-intake-of-calories-be/ link to info re Carbs - https://www.nhs.uk/live-well/healthy-weight/why-we-need-to-eat-carbs/ link to fats - https://www.nhs.uk/live-well/eat-well/different-fats-nutrition/ General good link = https://www.nhs.uk/live-well/eat-well/ Good link to breaking down the food groups i.e. dairy / fish/pulses etc https://www.nhs.uk/live-well/eat-well/the-eatwell-guide/ | Y | Added to help screen (final page) |  | Y | Great thanks
43 | JMcB Iphone | I think there may be an issue with Vitamin B1 calculations - it is always showing too low-- every single submission. Except one time I added a small % of something and I noticed it was 300% then I reduced that thing slowly and it went straight to 0% - unfortunately I cant rememeber what the combination was. Eggs are supposed to have Vitamin B1 but if I choose 100% eggs there is no B1 showing up. same for asparagus. Can you have a look at this and let me know why? | Y | This was indeed a bug, it has now been fixed | 13/03/2019 | y | FAb
43 | JMcB Iphone and Android | can the can of soda be swapped out with a glass of water/milk? | N | Water doesn't add any nutrients, so we think soda is a more common item that people might have with their meal. In future development I'd like to have dropdown menus for each item to provide more customisability.
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60